## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
all | Configure Maven and JavaFX base project | 1.5
| Design the main dashboard layout | 2
view all local containers | Implement Docker CLI command runner | 1.5
| Create the Container model class | 0.5
| Parse docker ps command output | 1
| Implement the container table UI | 2
| Add container list refresh behavior | 0.5
view container status | Display container status in the table (when selected) | 0.5
| Handle Docker unavailable errors | 1.5
start a stopped container | Implement the Docker start command | 0.5
| Add the start container button and action | 1.5
stop a running container | Implement the Docker stop command | 0.5
| Add the stop container button and action | 1.5
all | Write unit tests for Docker output parsing | 1.5
| Perform manual testing and update documentation | 1
Tests unitaires à chaque implémentations
| Estimate Totals | 17.5 | 0 | 0 | 0 | 0